## INSTRUCTIONS
The ARPA team provides updates to the Interim Finance Committee (IFC) at every meeting. Subrecipient Spend Plan updates are included in the report. Please provide updates by the deadline below: |  |  |  | IFC: | 2026-06-18
|  |  |  | DEADLINE: |  | All funds must be spent by: | 2026-12-31
|  |  |  | COUNTDOWN (from IFC): |  | 6 months 13 days
|  | Spend Plan updates due for JUNE IFC: | 2026-05-26
|  | Spend Plans are due by COB: | 2026-06-02
ARPA SUBRECIPIENT - SPEND PLAN UPDATE INSTRUCTIONS:
Complete Spend Plan based on applicable months remaining for each project period, allocating the UNSPENT BALANCE REMAINING.
The Total Reimbursements (Column AE) is based on RFR submittals received into the COVID Mailbox through 5/26/26.
Column AG is for any pending RFRs that have NOT been submitted to ARPA through APRIL 2026.
Columns AH through AP are for projections from MAY 2026 through the Project End Date.
Column AR is the check totals, which cannot exceed the unspent balance.
| Complete the Status and Comments columns. |  | Any projects with "zero" spend RFR's submitted for the last 2 months or more will require explaination and be prepared to DEOBLIGATE the unspent balance to allow GFO reallocating funding immediately.
The expectation is to complete monthly amounts based on the project expenditure timelines for reimbursements using spending trends, spending cycles and/or knowledge of ramping up expenditures.
Any amounts identified as spend plan savings/deobligations must be accompanied by a deobligating ACR with the accompanying work program due JUNE 25, 2026. This allows GFO to reallocate funding immediately.
Now is the time to Identify any delays and/or concerns about spending the balance remaining by your Project End Date.
Plan for JUNE 2026 IFC to be available for questions regarding your projects.
Send your responses to covid19@finance.nv.gov
For any questions, please reach out to Lesa Galloway, lgalloway@finance.nv.gov .

## PROJECTS (Active)
[13 empty] | 309617044.1 | 660000 | 5401607 | 8026445 | 10467738.4 | 2186587.5 | 0 | 26742377.9 | 282874666.2 | 0 | 422.52 | 18899694.08 | 50461449.5 | 73796126.67 | 70753607.53 | 0 | 213911300.3 | 68963365.9 | [11 empty] | 68440729.53
[10 empty] | #REF! | #REF! | #REF! | [9 empty] | 0 | 422.52 | 18899694.08 | 50461449.5 | 73796126.67 | 70753607.53 | 0 | RFR'S RECEIVED THROUGH 5/21/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 5/26/2026 FOR JULY-APRIL | 2026-05-16 | 2026-06-15 | 2026-07-15 | 2026-08-14 | 2026-09-13 | 2026-10-13 | 2026-11-12 | 2026-12-12 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
400 | DHHS | 23NVTRI01 | DHHS- DO | N/A | NEVADA TRANSPLANT INSTITUTE | 2022-10-20 | 2026-12-31 | 3195 | 39 | 15000000 |  |  | 15000000 | [6 empty] | 0 | 15000000 |  |  | 620663.74 | 7583393.67 | 2526979.11 | 3652695.49 |  | 14383732.01 | 616267.99 | 95.89% | 0 | 107717 | 97717 | 97717 | 97717 | 97717 | 97717 | 19965.99 | 0 | 0 | 616267.99 | 0 | On-Track | Renown is currently moving forward scheduling transplant #6 and they are awaiting CMS for the accrediting survey. NDN Donor Care Unit at 1050 E. Sahara Ave., has experienced a minor delay in consturction but is expected to be completed in 30 days.
402 | DHHS | 23EIPRC01 | DHHS- ADSD | N/A | EARLY INTERVENTION PERSONNEL CENTER | 2022-10-20 | 2026-06-30 | 3276 | 40 | 368100 |  |  | 368100 |  |  |  | 13339.4 |  |  | 13339.4 | 354760.6 |  |  | 16749.46 | 69421.2 | 155690.7 | 88333.33 |  | 330194.69 | 24565.91 | 93.08% | 6836.4 | 2026-05-16: 9115.2; 2026-06-15: 8614.31 |  | 24565.91 | 0 | On Track | Temporary contractor thorugh Manpower, Business Productivity Suite, and educational materials. The contractor will be compensated using the remaining project funds until those funds are fully exhausted.
402 | ADSD | 23CMSMI01 | DHHS-ADSD | N/A | Case Management System Modernization/Integration | 2024-02-08 | 2026-12-31 | 3151 | 41 | 7500000 |  |  | 7500000 | [6 empty] | 0 | 7500000 |  |  | 55865 | 367393.98 | 3197831.07 | 2033533.08 |  | 5654623.13 | 1845376.87 | 75.39% | 0 | 249747.5 | 249747.5 | 487147.5 | 249747.5 | 232179.33 | 220347.5 | 156460.04 | 0 | 0 | 1845376.87 | 0 | On Track | Note that the end date in this file was incorrect. NOA says 12/31/2026. Projection methodology: - Guidesoft Inc MSA Contractors based on monthly average through May - June 2026, with and increase in Julty for the start of hte year and reduced hours for Aug -Nov. 2026. - O365 based on monthly average costs. - Insight Public Sector based on contract deliverables. - Wellsky based on contract deliverables.
402 | ADSD | 23FCWPL01 | DHHS-ADSD | N/A | Personal Care Workforce Impact | 2022-10-20 | 2026-12-31 | 3278 | 62 | 5000000 |  |  | 5000000 | 0 |  | 2000000 |  |  |  | 2000000 | 3000000 |  |  |  | 5084.56 | 360844.62 | 889435.7 |  | 1255364.88 | 1744635.12 | 41.85% | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 164000 | 80635.12 | 0 | 1744635.12 | 0 | On Track | Projection methodology: Projection methodology: - Public Health Supportive based on project plan. - KPS3 based on project deliverable schedule.
402 | ADSD | 23HCAPD01 | DHHS-ADSD | N/A | Home/Chore Assistance for people with Disabilities | 2022-10-20 | 2026-09-30 | 3278 | 62 | 1559280 |  |  | 1559280 | 0 |  | 59280 |  |  |  | 59280 | 1500000 |  |  |  | 193311.08 | 916278.09 | 207135.16 |  | 1316724.33 | 183275.67 | 87.78% | 0 | 65000 | 65000 | 53275.67 | 0 | 0 |  |  |  |  | 183275.67 | 0 | On Track | Projection methodology: - Acumen Fiscal Agent based on monthly projections for self-directed service support (Monthly average used for May -July. 2026) - Washoe County based on projections for direct services, reflects the monthly average used for May -July. 2026) - Jewish Family Service Agency based on projections for monthly direct service and administrative cost (amount varies by month)
402 | ADSD | 23INHSV01 | DHHS-ADSD | N/A | In home Services, home modifications, assistive tech | 2022-10-20 | 2026-12-31 | 3278 | 62 | 2090000 |  |  | 2090000 | 0 |  | 59280 |  |  |  | 59280 | 2030720 |  |  |  | 1001269.81 | 942256.53 | 76700.5 |  | 2020226.84 | 10493.16 | 99.48% | 0 | 10493.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10493.16 | -1.4916e-10 | On Track | Working with subrecipient/provider to fix RFR errors before payment.
402 | ADSD | 23RFPCN01 | DHHS-ADSD | N/A | RFP Consultant for Intensive Behavioral Support Homes | 2022-10-20 | 2026-12-31 | 3279 | 34 | 14520000 |  |  | 14520000 |  |  | 2000000 |  | 1698250 |  | 3698250 | 10821750 |  |  |  | 185103.94 | 1468023.98 | 2880295.91 |  | 4533423.83 | 6288326.17 | 41.89% | 0 | 786040.77 | 786040.77 | 786040.77 | 786040.77 | 786040.77 | 786040.77 | 786040.77 | 786040.78 | 0 | 6288326.17 | 0 | On-track | We are expecting expenses due to participation incentives going out
402 | ADSD | 23RSBEX01 | DHHS-ADSD | N/A | Residential Setting Beds Expansion | 2022-10-20 | 2026-09-30 | 3278 | 63 | 4000000 |  |  | 4000000 | [6 empty] | 0 | 4000000 |  |  |  | 127023.52 | 3144731.74 | 715680.38 |  | 3987435.64 | 12564.36 | 99.69% | 0 | 12564.36 | 0 | 0 | 0 | 0 |  |  |  |  | 12564.36 | -3.3469e-10 | On Track | Subaward de-obligations
402 | ADSD | 23SVNEX01 | DHHS-ADSD | N/A | Service Navigation Expansion | 2022-10-20 | 2026-12-31 | 3278 | 62 | 1646881 |  |  | 1646881 | 0 |  | 500000 |  |  |  | 500000 | 1146881 |  |  |  | 225000 | 478445.96 | 163200.79 |  | 866646.75 | 280234.25 | 75.57% | 0 | 50500 | 50500 | 55000 | 55000 | 20000 | 20000 | 20000 | 9234.25 | 0 | 280234.25 | 0 | On Track | Projection methodology: - Money Management International based on monthly contract amount. - Jewish Family Service Agency, Lyon County, and Access to Healthcare Network based on remaining balance and award, split across remaining months. - KPS3 based on contract deliverables (Start date for additional deliverable in May. 2026, continuing through Dec. 2026.) - Nevada Public Health Foundation based on contract deliverables (Higher amount in May and Jun. 2026, other months in project period at $10k.)
406 | DPBH | 22BHCGM01 | DHHS-DPBH | N/A | CONTRACT MANAGEMENT SYSTEM | 2022-05-05 | 2026-06-30 | 3223 | 19 | 477606 |  |  | 477606 | [6 empty] | 0 | 477606 |  |  | 326628 | 60282 | 39664.2 | 120 |  | 426694.2 | 50911.8 | 89.34% | N/A | 810.23 | 5671.57 | 7082.5 | 7082.5 | 7082.5 | 7082.5 | 8050 | 8050 |  | 50911.8 | 0 | On Track | A request to extend the performance period to 12/30/26 has been submitted, to ensure that future approved Agate Change Requests will be able to be completed and paid for through 12/30/26. Funds were allocated to the Service Enhancement deliverable to pay for approved Change Requests.
406 | DPBH | 22BHSTF01b-c | DHHS-DPBH | N/A | DPBH STAFFING for ARPA Reporting-SFY24 & SFY25 | 2023-07-01 | 2027-03-31 | 3223 | 01 / 18 | 552445 | 404873 |  | 957318 | [6 empty] | 0 | 957318 |  |  |  | 249208.08 | 252955.18 | 207439.22 |  | 709602.48 | 247715.52 | 74.12% | N/A | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 71715.52 | 247715.52 | 0 | On Track | Project performance period extended for continued work and support of completing project tasks, Performing final reconcilliation, and submitting all final reporting. Project on-track to fully expend all funds. Projections based on current expenditure trends.
406 | DPBH | 23CFAEP01 | DHHS-DPBH | N/A | EPIDEMIOLOGIST | 2022-10-20 | 2026-12-31 | 3219 | 34 | 5000000 |  |  | 5000000 | [6 empty] | 0 | 5000000 |  |  | 5642.56 | 191705.75 | 1410887.74 | 1292032.13 |  | 2900268.18 | 2099731.82 | 58.01% | N/A | 190607.98 | 272731.97 | 272731.97 | 272731.97 | 272731.97 | 272731.97 | 272731.97 | 272732.02 |  | 2099731.82 | 0 | On Track | Kristen Clements-Nolle: PhD (3), MS HAB (6), MPH Epi (3), Grad Special MPH Epi (2), Epidemiology and Biostatistics Certificate (2), Grad Special Epi and Biostatistics Certificate (1), Online Public Health Data Management and Analysis Certificate (7), Undergraduate Public Health (7), Graduate Assistant MS HAB (3), Graduate Assistant MPH Epi (7), Graduate Assistant Online MPH (1). Brian Labus: All program staff, and all three member of cohort 2 are currently in the program. Two of three people from cohort 1 completed the 12 months, one left a month early to take a full time position. Projections based on previous expenditures and coordiation with subrecipient. Expected to fully ewxpend funds.
406 | DPBH | 23EMGCS01 | DHHS-DPBH-CRISIS RESPONSE | N/A | EMERGENCY CRISIS CARE (Transfer 5 million to DCFS) | 2022-07-01 | 2026-06-30 | 3165 | 64 | 10000000 |  |  | 10000000 | 0 | 5000000 | 1900000 |  |  |  | 6900000 | 3100000 |  |  | 57796.22 | 2079879 | 698605.6 | 249285.96 |  | 3085566.78 | 14433.22 | 99.53% | N/A | 2026-05-16: 957.22; 2026-06-15: 13476 |  | 14433.22 | 2.6012e-10 | On Track | This funding stream did receive a approved extension to end on June 30, 2026. Our Seven Hills provider was able to expend a majority of their award hoever it did end at the December. We are currently getting a new award for the remaining balance $13,476 to Desert Parkway to expend quickly before June 2026.
406 | DPBH | 23GIDTR01 | DHHS-DPBH | N/A | GENOMIC INFECTIOUS DISEASE TRACKING | 2022-10-20 | 2026-06-30 | 3219 | 35 | 1500000 |  |  | 1500000 | [6 empty] | 0 | 1500000 |  |  |  | 131435.79 | 943395.25 | 425168.62 |  | 1499999.66 | 0.34 | 100% | N/A | 2026-05-16: 0; 2026-06-15: 0 |  | 0 | -0.34 | On Track | Project Complete. Closeout activities in process.
406 | DPBH | 23HCWSS02 | DHHS-DPBH | N/A | Health Care Workforce Scholarships (Transferred from DHCFP) | 2023-06-14 | 2026-12-31 | 3234 | 22 | 5494300 |  |  | 5494300 | [6 empty] | 0 | 5494300 |  |  |  | 201861.5 | 1819585.17 | 2262469.92 |  | 4283916.59 | 1210383.41 | 77.97% | N/A | 147779.79 | 237668.36 | 147176.06 | 147176.06 | 147176.06 | 127802.36 | 127802.36 | 127802.36 |  | 1210383.41 | 0 | On Track | Healthy Communities Coalition 31 scholarship recipients total award. 100% spent down. UNR Larson Institute 26 scholarship recipients CHW, 15 English Doula, 17 Spanish Doula scholarship recipients, 20 scholarship applicants accepted training scholarships. UNR Integration 6 fellowships. Nevada Primary Care 11 Scholarships PCP’s, 1 Preceptor 1 MA learners, 9 EKG learners. High Sierra AHEC 15 scholarships for Spring 2026 semester. 5 Ambassadors, 1 Scholar. UNR CASAT Supervision: 13 new licensed PRSS-S; 1 new licensed ADG Supervisors. UNLV BeHere 23 scholarship recipients. UNR Resilience, Praveen: 9 Public Health Certificates, 9 Full time online MPH program. Dr. Sharma 154 (Undergraduate: 28; Master's: 64; Doctoral: 62); In addition, all total GA-ships have also been awarded: 15(Master's=9; Doctoral=6); Project is On Track and expected to fully spend down by end of project period.
406 | DPBH | 23IBCLC02 | DHHS-DPBH | N/A | International Board Certified Lactation Consultants | 2023-06-15 | 2026-12-31 | 3234 | 21 | 666000 |  | 0 | 666000 | [6 empty] | 0 | 666000 |  |  |  | 4997.96 | 157255.49 | 212652.28 |  | 374905.73 | 291094.27 | 56.29% | N/A | 23904.88 | 39841.5 | 39841.5 | 39841.5 | 39841.5 | 34613.09 | 34613.09 | 38597.21 |  | 291094.27 | 0 | On Track | UNLV Pipeline Southern Nevada latch clinic has officially started with adding two extra days that began on May 1st. One at the Healthy Living Institute, and adding another day at UNLV Pediatrics. The pathway 3 mentees have also attended a breastfeeding workshop hosted by the NV Breastfeeding Coalition to increase their knowledge and skill set. Has also been approached with the opportunity to work with the city of Henderson to have our mentees teach breastfeeding education this summer. Project is On Track and expected to fully spend down by end of project period.
406 | DPBH | 23LCCMS01 | DHHS-DPBH | N/A | Lakes Crossing Camera System | 2022-08-18 | 2026-04-30 | 3645 | 61 | 1462644 |  |  | 1462644 |  |  |  |  | 288337.5 |  | 288337.5 | 1174306.5 |  |  | 24377.24 | 103040.13 | 888600.13 | 115031.97 |  | 1131049.47 | 43257.03 | 96.32% | N/A | [9 empty] | 0 | -43257.03 | Savings Identified | The 23LCCMS01 project has been completed. A request to deobligate the remaining balance of $43,257.03 and redirect the savings to 24FPROS01 was submitted on 4/27/2026.
406 | DPBH | 23LRHA01 | DHHS-DPBH | N/A | Local & Regional Authorities Washoe, Carson, Churchill & SNHD (Merged) | 2022-08-17 | 2026-12-31 | 3234 | 23 | 20800000 |  |  | 20800000 | [6 empty] | 0 | 20800000 |  |  | 4661930.94 | 2517080.94 | 3263651.78 | 6352663.44 | 0 | 16795327.1 | 4004672.9 | 80.75% | N/A | 133067.72 | 399203.16 | 578733.67 | 578733.67 | 578733.67 | 723417.08 | 723417.09 | 289366.84 |  | 4004672.9 | 0 | On Track | Washoe: NNPH is on time and under budget - The ribbon cutting ceremony occurred April 23. An additional SOW has been submitted for review and approval. Carson: CCHHS On track for project completion in November 2026. Churchill: The project is 95% to completion. On target to complete project as expected.
406 | DPBH | 23NBSTR01 | DHHS-DPBH | N/A | UNR NSPHL Newborn | 2022-10-20 | 2026-10-31 | 3222 | 33 | 3953689 |  |  | 3953689 | [6 empty] | 0 | 3953689 |  |  |  | 820927.41 | 1889733.67 | 968761.76 |  | 3679422.84 | 274266.16 | 93.06% | N/A | 117895.36 | 13030.9 | 39092.7 | 19546.35 | 26061.8 | 58639.05 |  |  |  | 274266.16 | 0 |  | Spend down is on track; 3 of the 5 remaining disorders will be added to the panel after the building certificate of occupancy is granted in October 2026 as equipment can't be set up until they are in the new building. NSPHL states they will completely spend down by end of performance period.
406 | DPBH | 23RCCLV01 | DHHS-DPBH | N/A | RECUPERATIVE CARE CENTER EXPANSION | 2022-10-20 | 2026-09-30 | 3161 | 63 | 10000000 |  |  | 10000000 | [6 empty] | 0 | 10000000 |  |  |  | 0 | 1648607.93 | 7431628.33 |  | 9080236.26 | 919763.74 | 90.8% | N/A | 183952.75 | 275929.13 | 229940.94 | 137964.56 | 91976.36 |  |  |  |  | 919763.74 | 0 | On Track | Project is ongoing and spending has increased rapidly, with $9,080,236.26 in expenditures as of June, 2026. Expected to fully spend down by end of project period. Projections based previously expended funds and coordination with subrecipient.
406 | DPBH | 23RHSCC01 | DHHS-DPBH | N/A | Reproductive Health Services | 2023-01-01 | 2026-12-31 | 3224 | 01, 15 | 6446148 |  |  | 6446148 | [6 empty] | 0 | 6446148 |  |  | 105015.49 | 1191335.83 | 1489526.75 | 774530.1 |  | 3560408.17 | 2885739.83 | 55.23% | N/A | 71591.84 | 365368.85 | 408129.86 | 408129.86 | 408129.86 | 408129.86 | 408129.86 | 408129.84 |  | 2885739.83 | 0 | On Track | All three subgrantees have submitted spend plans for the entirety of the project period; spend plans submitted are based by SFY, hence the projections have been broken out monthly based on subrecipients projections. Spend plans ascertain they will fully expend their award amounts by the end of the project period, December 31, 2026.
406 | DPBH | 24FPROS01 | DHHS-DPBH | N/A | Forensic Professional Services - Lake Crossing | 2023-12-13 | 2026-12-31 | 3645 | 62 | 4920000 |  |  | 4920000 | 660000 |  | 744094 |  |  |  | 1404094 | 3515906 |  |  |  | 127478.69 | 1251293.04 | 1132091.15 |  | 2510862.88 | 1005043.12 | 71.41% | N/A | 125630.39 | 125630.39 | 125630.39 | 125630.39 | 125630.39 | 125630.39 | 125630.39 | 125630.39 |  | 1005043.12 | 0 | On Track | Project is on track and has become destination for de-obligated funds to support ability to spend. A request to deobligate the remaining balance of $43,257.03 from 23LCCMS01 and redirect the savings to 24FPROS01 was submitted on 4/27/2026. A request is to transfer $479,379 from 24SNFLT01 to 24FPROS01. The associated work programs (#27FRF31611 and #27FRF36452) are in process. Additional allocations to spend plan will be included in projections when funds become available for project.
406 | DPBH | 24JBMHP01 | DHHS-DPBH | N/A | Forensic Jail Based Mental Health Programs (SNAMHS/NNAMHS) | 2023-12-13 | 2026-12-31 | 3161 | 64 | 14905281 | 3691097.1 |  | 18596378.1 | [6 empty] | 0 | 18596378.1 |  |  |  | 375456.73 | 9082223.3 | 4927185.01 |  | 14384865.04 | 4211513.06 | 77.35% | N/A | 1121255.6 | 735775.59 | 631540.71 | 564094.62 | 441465.35 | 340290.2 | 266724.65 | 110366.34 |  | 4211513.06 | 0 | On Track | Project is on track to fully spend down by the end of the performance period. Continues to be an option for re-allocated funds due to continued ability to spend additional funds.
406 | DPBH | 24SNFLT01 | DHHS-DPBH | N/A | Skilled Nursing Facility - Forensic Long-Term Care | 2023-11-17 | 2026-12-31 | 3161 | 65 | 5716150 |  |  | 5716150 |  |  | 593974 | 2721280 |  |  | 3315254 | 2400896 |  |  |  | 192214.88 | 644083.94 | 489676.1 |  | 1325974.92 | 1074921.08 | 55.23% | N/A | 115504.2 | 106659.86 | 62229.67 | 62229.67 | 62229.67 | 62229.67 | 62229.67 | 62229.67 |  | 595542.08 | -479379 | Savings Identified | 24SNFLT01 savings are due to competitive rates with current community providers. A request is to transfer $479,379 from 24SNFLT01 to 24FPROS01. The associated work programs (#27FRF31611 and #27FRF36452) are in process.
407 | DWSS | 23ACNVM01 | DHHS-DSS | N/A | ACCESS NEVADA MODERNIZATION No Wrong Door Single Web Portal | 2022-10-25 | 2026-12-31 | 3228 | 53 | 3112296 |  | 9387704 | 12500000 | [6 empty] | 0 | 12500000 |  |  |  | 4148997.17 | 3964544.82 | 1894081.81 |  | 10007623.8 | 2492376.2 | 80.06% | 0 | 184527.06 | 1637126 | 350625 | 111787 | 124320 | 83991.14 | 0 | 0 |  | 2492376.2 | 0 | On Track | Projections are based on monthly deliverables and remaining billing to address M&O production defect resolution through 12/31/2026
407 | DSS | 23CHDIF01 | DHHS-DSS | N/A | CHILD CARE INFRASTRUCTURE | 2022-05-06 | 2026-12-31 | 3267 | 55 | 30000000 |  |  | 30000000 | [6 empty] | 0 | 30000000 |  |  | 8455742.56 | 11363038.52 | 5323464.92 | 3958163.78 |  | 29100409.78 | 899590.22 | 97% | 0 | 387477.73 | 343559.14 | 138953.84 | 10008.64 | 9757.79 | 6256.84 | 3576.24 |  |  | 899590.22 | 1.1642e-09 | On Track | All subrecipients are on track for spending.
407 | DSS | 23NOMAD01 | DHHS-DSS | N/A | NOMADS MODERNIZATION | 2022-10-20 | 2026-12-31 | 3228 | 64 | 48510328 |  |  | 48510328 | [6 empty] | 0 | 48510328 |  |  | 2963017.72 | 6787741.04 | 10541855.11 | 13551074.37 |  | 33843688.24 | 14666639.76 | 69.77% | 0 | 508374.82 | 5562588.36 | 2517341.9 | 2517341.9 | 1517341.9 | 1475709.88 | 317941 | 250000 |  | 14666639.76 | 0 | On Track | Projections are based on monthly contractual/MSA deliverables, Phase III and M&O production defect resolution through 12/31/2026
409 | DCFS | 22DSWHD01 | DHHS-DCFS-SNCAS | N/A | DESERT WILLOW HARDENING CIP#: 22-A012 Ceiling Replacement | 2022-04-07 | 2026-12-31 | 3646 | 48 | 916718 |  |  | 916718 | [6 empty] | 0 | 916718 |  | 422.52 | 71653.31 | 139935.27 | 244571.99 | 21792.06 |  | 478375.15 | 438342.85 | 52.18% | 0 | 54792.86 | 54792.86 | 54792.86 | 54792.86 | 54792.86 | 54792.86 | 54792.86 | 54792.83 | 0 | 438342.85 | 0 | On Track | Construction has resumed, expect large invoices to be submitted soon.
409 | DCFS | 22DSWHD01a | DHHS-DCFS-SNCAS | N/A | DESERT WILLOW HARDENING CIP Project#: 23-A005 Anti-Ligature & Unit Hardening | 2022-08-18 | 2026-12-31 | 3646 | 49 | 5072061 |  |  | 5072061 | [6 empty] | 0 | 5072061 |  |  | 155077.8 | 1178187.53 | 1203299.41 | 975949.58 |  | 3512514.32 | 1559546.68 | 69.25% | 0 | 194943.34 | 194943.34 | 194943.34 | 194943.34 | 194943.34 | 194943.34 | 194943.34 | 194943.3 | 0 | 1559546.68 | 0 | On Track | Construction has resumed, expect large invoices to be submitted soon.
409 | DCFS | 23CLKCW01 | DHHS-DCFS | N/A | CLARK COUNTY CHILD WELFARE | 2022-08-18 | 2026-06-30 | 3145 | 44 | 4198804 |  |  | 4198804 | [6 empty] | 0 | 4198804 |  |  |  | 769154.54 | 106694 | 2160818.5 |  | 3036667.04 | 1162136.96 | 72.32% | 0 | 2026-05-16: 185919; 2026-06-15: 325406; 2026-07-15: 325406; 2026-08-14: 325405.96 |  | 1162136.96 | 0 | On Track | A request to extend the performance period to 8/31/26 will be submitted to the ARPA team so Clark County can fully expend their award. Projections based on remaining funds through August 2026.
409 | DCFS | 23EMGCS02 | DHHS-DCFS | N/A | EMERGENCY FUNDING FOR CHILD AND FAMILY SERVICES | 2023-01-31 | 2026-06-30 | 3145 | 52 | 5000000 |  |  | 5000000 | [6 empty] | 0 | 5000000 |  |  | 68238.71 | 1386373.2 | 2608138.27 | 426459.48 | 0 | 4489209.66 | 510790.34 | 89.78% | 0 | 2026-05-16: 0; 2026-06-15: 510790.34 |  | 510790.34 | 0 | On Track | Projections based on the adjusted monthly flat fee of the Magellan contract of $190,000 a month from April 2026 to November 2026 and $169,087.54 a month for December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The June projection includes the expenses from April through June 2026.
409 | DCFS | 23FTFPS01 | DHHS-DCFS | N/A | FAMILY TO PEER SUPPORT | 2022-08-18 | 2026-12-31 | 3145 3146-FY24 | 42 | 977346 |  | 980629 | 1957975 |  |  | 49755 |  |  |  | 49755 | 1908220 |  |  | 113037.71 | 618345.64 | 719912.25 | 450195.25 |  | 1901490.85 | 6729.15 | 99.65% | 0 | 6728.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 6729.15 | 9.2768e-11 | On Track | Project Complete. Closeout activities in progress once May RFR is processed.
409 | DCFS | 23IFIHS01 | DHHS-DCFS | N/A | INTENSIVE FAMILY IN HOME SERVICES | 2022-10-20 | 2026-12-31 | 3145 3146-FY24 | 01 41 | 2431165 | 91031 | 2474401 | 4996597 |  |  | 120062 | 1250000 |  |  | 1370062 | 3626535 |  |  | 0 | 825501.65 | 1483975.81 | 470000 |  | 2779477.46 | 847057.54 | 76.64% | 0 | 0 | 34604 | 135000 | 135000 | 135000 | 135000 | 135000 | 137453.54 | 0 | 847057.54 | 0 | on Track | Projections based on the adjusted monthly flat fee of the Magellan contract of $190,000 a month from April 2026 to November 2026 and $169,087.54 a month for December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The June projection includes the expenses from April through June 2026.
409 | DCFS | 23LVSRC01 | DHHS-DCFS | N/A | VEGAS STRONG RESILIENCY CENTER | 2022-12-15 | 2026-06-30 | 3145 | 68 | 7022777 |  |  | 7022777 |  | 401607 |  |  |  |  | 401607 | 6621170 |  |  | 0 | 196177.75 | 644440 | 5758379.39 |  | 6598997.14 | 22172.86 | 99% | 0 | 2121.71 | 4011.15 | 4010 | 4010 | 4010 | 4010 |  |  |  | 22172.86 | -3.3469e-10 | On Track | Project is in process with completion expected in October 2026, monitoring of the project continues. Extension request will be submitted to the ARPA team to extend subaward to October 31, 2026
409 | DCFS | 23NWFEO01 | DHHS-DCFS | N/A | Nursing Workforce Educational Opportunity | 2022-10-20 | 2026-09-30 | 3145 | 66 | 6000000 |  |  | 6000000 | 0 | [5 empty] | 0 | 6000000 |  |  | 1189702.67 | 2364177.05 | 390185.8 | 2031650.45 |  | 5975715.97 | 24284.03 | 99.6% | 0 | 0 | 0 | 0 | 0 | 24284.03 | 0 |  |  |  | 24284.03 | -2.6193e-10 | On Track | Projections are based on scholarship support for APRN students by semester for the Summer 2026 semester.
409 | DCFS | 23SUPST3145 | DHHS-DCFS | N/A | ARPA OVERSIGHT (8 FTE Support Positions) | 2024-07-01 | 2027-02-28 | 3145 | 01, 43 | 1014987 |  | 232771 | 1247758 |  |  |  |  | 200000 |  | 200000 | 1047758 |  |  |  |  | 938792.53 | 69407.94 |  | 1008200.47 | 39557.53 | 96.22% | 0 | 0 | 10000 | 10000 | 10000 | 9557.53 | 0 | 0 | 0 | 0 | 39557.53 | 0 | On Track | This project oversees ARPA projects to provide support in the areas of fiscal, reporting, subrecipient monitoring, grants management, contract management and human resources to comply with federal and state regulations. The amounts projected each month are based on current spending trends for 1 temp contractor
409 | DCFS | 23SUPST3146 | DHHS-DCFS | N/A | CHILDRENS BEHAVIORAL HEALTH AUTHORITY (8 FTE Support Positions) | 2024-07-01 | 2027-02-28 | 3146 | 01, 43 | 1499500 |  |  | 1499500 |  |  |  | 232771 |  |  | 232771 | 1266729 |  |  |  |  | 1041847.17 | 218778.59 |  | 1260625.76 | 6103.24 | 99.52% | 0 | 0 | 6103.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6103.24 | 9.0949e-12 | On Track | Project Complete. Closeout activities in progress once May RFR is processed.
409 | DCFS | 23UNITY01 | DHHS-DCFS | N/A | UNITY Replacement | 2022-10-21 | 2026-12-31 | 3143 | 41 | 18370000 |  |  | 18370000 | [6 empty] | 0 | 18370000 |  |  | 8554.95 | 134739.35 | 1523983.62 | 85110 |  | 1752387.92 | 16617612.08 | 9.539% | 0 | 0 | 1001100 | 4493782.08 | 1875381 | 1875381 | 1875381 | 1875381 | 3621206 | 0 | 16617612.08 | 0 | On Track | New contract to provide design, development, and implementation services for a new comprehensive child welfare information system was approved at May BOE. Kickoff meeting scheduled for 06/8/26. Projections are based on CCWIS budget for design and implementation, project management and independent valuation.
409 | DCFS | 23WINIC01 | DHHS-DCFS | N/A | Wraparound Authority/ intensive Care Coordination | 2022-08-18 | 2026-12-31 | 3145-FY23, 3146-FY24 | 01, 40 | 7314984 |  | 7335048 | 14650032 |  |  |  | 6250348 |  |  | 6250348 | 8399684 |  |  |  | 2545174.34 | 4389270 | 1134000 |  | 8068444.34 | 331239.66 | 96.06% | 0 | 0 | 24605.66 | 55000 | 55000 | 55000 | 55000 | 55000 | 31634 | 0 | 331239.66 | 0 | On Track | Projections based on the adjusted monthly flat fee of the Magellan contract of $190,000 a month from April 2026 to November 2026 and $169,087.54 a month for December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The June projection includes the expenses from April through June 2026.
[13 empty] | 309617044.1 | 660000 | 5401607 | 8026445 | 10467738.4 | 2186587.5 | 0 | 26742377.9 | 282874666.2 | 0 | 422.52 | 18899694.08 | 50461449.5 | 73796126.67 | 70753607.53 | 0 | 213911300.3 | 68963365.9 |  | 6836.4 | 5321021.22 | 13830236.95 | 12573165.93 | 9117337.12 | 7613384.68 | 7441756.5 | 5834430.32 | 6630844.49 | 71715.92 | 68440729.53 | -522636.37
[31 empty] | ck | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on R5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Partial DEOB $13,339.40 WP#26FRF32762
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 3266 to 3278 in FY24
Note on Q7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deob WP of WP24FRF32784
Note on I8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Danette M. Kluever: Moved from BA3266 to BA3278 in SFY24
Note on Q8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deob WP 24FRF32787
Note on I9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Danette M. Kluever: Moved from BA3266 to BA3278 in SFY24
Note on Q9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DeOb WP24FRF32786
Note on S10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WP26FRF32793 Partial DEOB $1,098,249.81 FEB IFC Reply: WP26FRF32794 Partial DEOB/Redirect $600,000 to 24CMH9A01 Campus for Hope APR IFC
Note on I11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to BA3278 eff FY24, no Exp in FY23 to BA3266
Note on I12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to BA3278 eff FY24, no Exp in FY23 to BA3266
Note on Q12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SFY 24 De-Ob #24FRF32785
Note on P16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending Grant Realignment WP for $2,896,697 reduction in authority (DK) Reply: $5,000,000 - transferred to DCFS under WP# 23FR314521
Note on Q16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agency Submitted DeOb for $2,896,697 that was signed off. Agency sent email to the COVID19 mailbox Requesting to Retract DeOB. Dan told Amy @ ARPA Admin Mtng 3.14.24 and she is checking with Jim Wells. Reply: $2.8 retracted but agency is giving up 1.9 per J. Wells. WP 24FR316504 (-903,303) combined with an L01 of 3,945,507 reduces the award by the 1.9 million. Reply: WP #24FR316504 $903,303
Note on S20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Partial Deob $288,337.50 Transfer to Jail Based 24JBMHP01
Note on O25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deob WP 24FRF36453
Note on Q25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: De-Obligation #24FR132776 $744,094 - June 2024 IFC Reply: Agency De-Ob WP# 24FRF36454
Note on L26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Supplemental#1=$2,939,148 & Supplemental #2 =$221,588.96 Supplemental #3= $530,360.14 Reply: Supplemental #2+#3 = $751,950.10 26FRF31613 FEB-IFC
Note on Q27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WP#24FR132777 De-Obligation $2,070,848 June 2024 IFC Reply: Agency De-Ob WP#24FRF31618 - Revised to $593,974
Note on U27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WP#24FRF31618 June 2024 IFC
Note on M38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: L01
Note on P38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FY23 not spent and not balanced foward
Note on S39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deob $200,000 FEB26 IFC

## DHHS-DO
[13 empty] | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 0 | 0 | 620663.74 | 7583393.67 | 2526979.11 | 3652695.49 | 0 | 14383732.01 | 616267.99 | [11 empty] | 616267.99
[10 empty] | #REF! | #REF! | #REF! | [9 empty] | 0 | 0 | 620663.74 | 7583393.67 | 2526979.11 | 3652695.49 | 0 | RFR'S RECEIVED THROUGH 5/21/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 5/26/2026 FOR JULY-APRIL | 2026-05-16 | 2026-06-15 | 2026-07-15 | 2026-08-14 | 2026-09-13 | 2026-10-13 | 2026-11-12 | 2026-12-12 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
400 | DHHS | 23NVTRI01 | DHHS- DO | N/A | NEVADA TRANSPLANT INSTITUTE | 2022-10-20 | 2026-12-31 | 3195 | 39 | 15000000 |  |  | 15000000 | [6 empty] | 0 | 15000000 |  |  | 620663.74 | 7583393.67 | 2526979.11 | 3652695.49 |  | 14383732.01 | 616267.99 | 95.89% |  | 107717 | 97717 | 97717 | 97717 | 97717 | 97717 | 19965.99 |  |  | 616267.99 | 0 | On-Track | Renown is currently moving forward scheduling transplant #6 and they are awaiting CMS for the accrediting survey. NDN Donor Care Unit at 1050 E. Sahara Ave., has experienced a minor delay in consturction but is expected to be completed in 30 days.
[13 empty] | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 0 | 0 | 620663.74 | 7583393.67 | 2526979.11 | 3652695.49 | 0 | 14383732.01 | 616267.99 |  | 0 | 107717 | 97717 | 97717 | 97717 | 97717 | 97717 | 19965.99 | 0 | 0 | 616267.99 | 0

## ADSD
[13 empty] | 36684261 | 0 | 0 | 4618560 | 13339.4 | 1698250 | 0 | 6330149.4 | 30354111.6 | 0 | 0 | 72614.46 | 2173608.09 | 10664102.69 | 7054314.85 | 0 | 19964640.09 | 10389471.51 | [11 empty] | 10389471.51
[10 empty] | #REF! | #REF! | #REF! | [9 empty] | 0 | 0 | 72614.46 | 2173608.09 | 10664102.69 | 7054314.85 | 0 | RFR'S RECEIVED THROUGH 5/21/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 5/26/2026 FOR JULY-APRIL | 2026-05-16 | 2026-06-15 | 2026-07-15 | 2026-08-14 | 2026-09-13 | 2026-10-13 | 2026-11-12 | 2026-12-12 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
402 | DHHS | 23EIPRC01 | DHHS- ADSD | N/A | EARLY INTERVENTION PERSONNEL CENTER | 2022-10-20 | 2026-06-30 | 3276 | 40 | 368100 |  |  | 368100 |  |  |  | 13339.4 |  |  | 13339.4 | 354760.6 |  |  | 16749.46 | 69421.2 | 155690.7 | 88333.33 |  | 330194.69 | 24565.91 | 93.08% | 6836.4 | 2026-05-16: 9115.2; 2026-06-15: 8614.31 |  | 24565.91 | 0 | On Track | Temporary contractor thorugh Manpower, Business Productivity Suite, and educational materials. The contractor will be compensated using the remaining project funds until those funds are fully exhausted.
402 | ADSD | 23CMSMI01 | DHHS-ADSD | N/A | Case Management System Modernization/Integration | 2024-02-08 | 2026-12-31 | 3151 | 41 | 7500000 |  |  | 7500000 | [6 empty] | 0 | 7500000 |  |  | 55865 | 367393.98 | 3197831.07 | 2033533.08 |  | 5654623.13 | 1845376.87 | 75.39% |  | 249747.5 | 249747.5 | 487147.5 | 249747.5 | 232179.33 | 220347.5 | 156460.04 |  |  | 1845376.87 | 0 | On Track | Note that the end date in this file was incorrect. NOA says 12/31/2026. Projection methodology: - Guidesoft Inc MSA Contractors based on monthly average through May - June 2026, with and increase in Julty for the start of hte year and reduced hours for Aug -Nov. 2026. - O365 based on monthly average costs. - Insight Public Sector based on contract deliverables. - Wellsky based on contract deliverables.
402 | ADSD | 23FCWPL01 | DHHS-ADSD | N/A | Personal Care Workforce Impact | 2022-10-20 | 2026-12-31 | 3278 | 62 | 5000000 |  |  | 5000000 | 0 |  | 2000000 |  |  |  | 2000000 | 3000000 |  |  |  | 5084.56 | 360844.62 | 889435.7 |  | 1255364.88 | 1744635.12 | 41.85% |  | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 164000 | 80635.12 |  | 1744635.12 | 0 | On Track | Projection methodology: Projection methodology: - Public Health Supportive based on project plan. - KPS3 based on project deliverable schedule.
402 | ADSD | 23HCAPD01 | DHHS-ADSD | N/A | Home/Chore Assistance for people with Disabilities | 2022-10-20 | 2026-09-30 | 3278 | 62 | 1559280 |  |  | 1559280 | 0 |  | 59280 |  |  |  | 59280 | 1500000 |  |  |  | 193311.08 | 916278.09 | 207135.16 |  | 1316724.33 | 183275.67 | 87.78% |  | 2026-05-16: 65000; 2026-06-15: 65000; 2026-07-15: 53275.67 |  | 183275.67 | 0 | On Track | Projection methodology: - Acumen Fiscal Agent based on monthly projections for self-directed service support (Monthly average used for May -July. 2026) - Washoe County based on projections for direct services, reflects the monthly average used for May -July. 2026) - Jewish Family Service Agency based on projections for monthly direct service and administrative cost (amount varies by month)
402 | ADSD | 23INHSV01 | DHHS-ADSD | N/A | In home Services, home modifications, assistive tech | 2022-10-20 | 2026-12-31 | 3278 | 62 | 2090000 |  |  | 2090000 | 0 |  | 59280 |  |  |  | 59280 | 2030720 |  |  |  | 1001269.81 | 942256.53 | 76700.5 |  | 2020226.84 | 10493.16 | 99.48% |  | 2026-05-16: 10493.16 |  | 10493.16 | -1.4916e-10 | On Track | Working with subrecipient/provider to fix RFR errors before payment.
402 | ADSD | 23RFPCN01 | DHHS-ADSD | N/A | RFP Consultant for Intensive Behavioral Support Homes | 2022-10-20 | 2026-12-31 | 3279 | 34 | 14520000 |  |  | 14520000 |  |  | 2000000 |  | 1698250 |  | 3698250 | 10821750 |  |  |  | 185103.94 | 1468023.98 | 2880295.91 |  | 4533423.83 | 6288326.17 | 41.89% |  | 786040.77 | 786040.77 | 786040.77 | 786040.77 | 786040.77 | 786040.77 | 786040.77 | 786040.78 | 0 | 6288326.17 | 0 | On-track | We are expecting expenses due to participation incentives going out
402 | ADSD | 23RSBEX01 | DHHS-ADSD | N/A | Residential Setting Beds Expansion | 2022-10-20 | 2026-09-30 | 3278 | 63 | 4000000 |  |  | 4000000 | [6 empty] | 0 | 4000000 |  |  |  | 127023.52 | 3144731.74 | 715680.38 |  | 3987435.64 | 12564.36 | 99.69% |  | 2026-05-16: 12564.36 |  | 12564.36 | -3.3469e-10 | On Track | Subaward de-obligations
402 | ADSD | 23SVNEX01 | DHHS-ADSD | N/A | Service Navigation Expansion | 2022-10-20 | 2026-12-31 | 3278 | 62 | 1646881 |  |  | 1646881 | 0 |  | 500000 |  |  |  | 500000 | 1146881 |  |  |  | 225000 | 478445.96 | 163200.79 |  | 866646.75 | 280234.25 | 75.57% |  | 50500 | 50500 | 55000 | 55000 | 20000 | 20000 | 20000 | 9234.25 |  | 280234.25 | 0 | On Track | Projection methodology: - Money Management International based on monthly contract amount. - Jewish Family Service Agency, Lyon County, and Access to Healthcare Network based on remaining balance and award, split across remaining months. - KPS3 based on contract deliverables (Start date for additional deliverable in May. 2026, continuing through Dec. 2026.) - Nevada Public Health Foundation based on contract deliverables (Higher amount in May and Jun. 2026, other months in project period at $10k.)
[13 empty] | 36684261 | 0 | 0 | 4618560 | 13339.4 | 1698250 | 0 | 6330149.4 | 30354111.6 | 0 | 0 | 72614.46 | 2173608.09 | 10664102.69 | 7054314.85 | 0 | 19964640.09 | 10389471.51 |  | 6836.4 | 1433460.99 | 1409902.58 | 1631463.94 | 1340788.27 | 1288220.1 | 1276388.27 | 1126500.81 | 875910.15 | 0 | 10389471.51 | -4.8385e-10
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Partial DEOB $13,339.40 WP#26FRF32762
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 3266 to 3278 in FY24
Note on Q6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deob WP of WP24FRF32784
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Danette M. Kluever: Moved from BA3266 to BA3278 in SFY24
Note on Q7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deob WP 24FRF32787
Note on I8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Danette M. Kluever: Moved from BA3266 to BA3278 in SFY24
Note on Q8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DeOb WP24FRF32786
Note on S9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WP26FRF32793 Partial DEOB $1,098,249.81 FEB IFC Reply: WP26FRF32794 Partial DEOB/Redirect $600,000 to 24CMH9A01 Campus for Hope APR IFC
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to BA3278 eff FY24, no Exp in FY23 to BA3266
Note on I11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to BA3278 eff FY24, no Exp in FY23 to BA3266
Note on Q11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SFY 24 De-Ob #24FRF32785

## DCFS
[13 empty] | 70932222 | 0 | 401607 | 169817 | 7733119 | 200000 | 0 | 8504543 | 62427679 | 0 | 422.52 | 1606265.15 | 10157766.32 | 15295110.85 | 13802541.24 | 0 | 40862106.08 | 21565572.92 | [11 empty] | 21565572.92
[10 empty] | #REF! | #REF! | #REF! | [9 empty] | 0 | 422.52 | 1606265.15 | 10157766.32 | 15295110.85 | 13802541.24 | 0 | RFR'S RECEIVED THROUGH 5/21/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 5/26/2026 FOR JULY-APRIL | 2026-05-16 | 2026-06-15 | 2026-07-15 | 2026-08-14 | 2026-09-13 | 2026-10-13 | 2026-11-12 | 2026-12-12 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
409 | DCFS | 22DSWHD01 | DHHS-DCFS-SNCAS | N/A | DESERT WILLOW HARDENING CIP#: 22-A012 Ceiling Replacement | 2022-04-07 | 2026-12-31 | 3646 | 48 | 916718 |  |  | 916718 | [6 empty] | 0 | 916718 |  | 422.52 | 71653.31 | 139935.27 | 244571.99 | 21792.06 |  | 478375.15 | 438342.85 | 52.18% |  | 54792.86 | 54792.86 | 54792.86 | 54792.86 | 54792.86 | 54792.86 | 54792.86 | 54792.83 |  | 438342.85 | 0 | On Track | Construction has resumed, expect large invoices to be submitted soon.
409 | DCFS | 22DSWHD01a | DHHS-DCFS-SNCAS | N/A | DESERT WILLOW HARDENING CIP Project#: 23-A005 Anti-Ligature & Unit Hardening | 2022-08-18 | 2026-12-31 | 3646 | 49 | 5072061 |  |  | 5072061 | [6 empty] | 0 | 5072061 |  |  | 155077.8 | 1178187.53 | 1203299.41 | 975949.58 |  | 3512514.32 | 1559546.68 | 69.25% |  | 194943.34 | 194943.34 | 194943.34 | 194943.34 | 194943.34 | 194943.34 | 194943.34 | 194943.3 |  | 1559546.68 | 0 | On Track | Construction has resumed, expect large invoices to be submitted soon.
409 | DCFS | 23CLKCW01 | DHHS-DCFS | N/A | CLARK COUNTY CHILD WELFARE | 2022-08-18 | 2026-06-30 | 3145 | 44 | 4198804 |  |  | 4198804 | [6 empty] | 0 | 4198804 |  |  |  | 769154.54 | 106694 | 2160818.5 |  | 3036667.04 | 1162136.96 | 72.32% |  | 2026-05-16: 185919; 2026-06-15: 325406; 2026-07-15: 325406; 2026-08-14: 325405.96 |  | 1162136.96 | 0 | On Track | A request to extend the performance period to 8/31/26 will be submitted to the ARPA team so Clark County can fully expend their award. Projections based on remaining funds through August 2026.
409 | DCFS | 23EMGCS02 | DHHS-DCFS | N/A | EMERGENCY FUNDING FOR CHILD AND FAMILY SERVICES | 2023-01-31 | 2026-06-30 | 3145 | 52 | 5000000 |  |  | 5000000 | [6 empty] | 0 | 5000000 |  |  | 68238.71 | 1386373.2 | 2608138.27 | 426459.48 | 0 | 4489209.66 | 510790.34 | 89.78% |  | 2026-05-16: 0; 2026-06-15: 510790.34 |  | 510790.34 | 0 | On Track | Projections based on the adjusted monthly flat fee of the Magellan contract of $190,000 a month from April 2026 to November 2026 and $169,087.54 a month for December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The June projection includes the expenses from April through June 2026.
409 | DCFS | 23FTFPS01 | DHHS-DCFS | N/A | FAMILY TO PEER SUPPORT | 2022-08-18 | 2026-12-31 | 3145 3146-FY24 | 42 | 977346 |  | 980629 | 1957975 |  |  | 49755 |  |  |  | 49755 | 1908220 |  |  | 113037.71 | 618345.64 | 719912.25 | 450195.25 |  | 1901490.85 | 6729.15 | 99.65% |  | 6728.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 6729.15 | 9.2768e-11 | On Track | Project Complete. Closeout activities in progress once May RFR is processed.
409 | DCFS | 23IFIHS01 | DHHS-DCFS | N/A | INTENSIVE FAMILY IN HOME SERVICES | 2022-10-20 | 2026-12-31 | 3145 3146-FY24 | 01 41 | 2431165 | 91031 | 2474401 | 4996597 |  |  | 120062 | 1250000 |  |  | 1370062 | 3626535 |  |  | 0 | 825501.65 | 1483975.81 | 470000 |  | 2779477.46 | 847057.54 | 76.64% |  |  | 34604 | 135000 | 135000 | 135000 | 135000 | 135000 | 137453.54 |  | 847057.54 | 0 | on Track | Projections based on the adjusted monthly flat fee of the Magellan contract of $190,000 a month from April 2026 to November 2026 and $169,087.54 a month for December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The June projection includes the expenses from April through June 2026.
409 | DCFS | 23LVSRC01 | DHHS-DCFS | N/A | VEGAS STRONG RESILIENCY CENTER | 2022-12-15 | 2026-06-30 | 3145 | 68 | 7022777 |  |  | 7022777 |  | 401607 |  |  |  |  | 401607 | 6621170 |  |  | 0 | 196177.75 | 644440 | 5758379.39 |  | 6598997.14 | 22172.86 | 99% |  | 2121.71 | 4011.15 | 4010 | 4010 | 4010 | 4010 |  |  |  | 22172.86 | -3.3469e-10 | On Track | Project is in process with completion expected in October 2026, monitoring of the project continues. Extension request will be submitted to the ARPA team to extend subaward to October 31, 2026
409 | DCFS | 23NWFEO01 | DHHS-DCFS | N/A | Nursing Workforce Educational Opportunity | 2022-10-20 | 2026-09-30 | 3145 | 66 | 6000000 |  |  | 6000000 | 0 | [5 empty] | 0 | 6000000 |  |  | 1189702.67 | 2364177.05 | 390185.8 | 2031650.45 |  | 5975715.97 | 24284.03 | 99.6% |  | 2026-09-13: 24284.03 |  | 24284.03 | -2.6193e-10 | On Track | Projections are based on scholarship support for APRN students by semester for the Summer 2026 semester.
409 | DCFS | 23SUPST3145 | DHHS-DCFS | N/A | ARPA OVERSIGHT (8 FTE Support Positions) | 2024-07-01 | 2027-02-28 | 3145 | 01, 43 | 1014987 |  | 232771 | 1247758 |  |  |  |  | 200000 |  | 200000 | 1047758 |  |  |  |  | 938792.53 | 69407.94 |  | 1008200.47 | 39557.53 | 96.22% |  | 2026-06-15: 10000; 2026-07-15: 10000; 2026-08-14: 10000; 2026-09-13: 9557.53 |  | 39557.53 | 0 | On Track | This project oversees ARPA projects to provide support in the areas of fiscal, reporting, subrecipient monitoring, grants management, contract management and human resources to comply with federal and state regulations. The amounts projected each month are based on current spending trends for 1 temp contractor
409 | DCFS | 23SUPST3146 | DHHS-DCFS | N/A | CHILDRENS BEHAVIORAL HEALTH AUTHORITY (8 FTE Support Positions) | 2024-07-01 | 2027-02-28 | 3146 | 01, 43 | 1499500 |  |  | 1499500 |  |  |  | 232771 |  |  | 232771 | 1266729 |  |  |  |  | 1041847.17 | 218778.59 |  | 1260625.76 | 6103.24 | 99.52% |  | 2026-06-15: 6103.24 |  | 6103.24 | 9.0949e-12 | On Track | Project Complete. Closeout activities in progress once May RFR is processed.
409 | DCFS | 23UNITY01 | DHHS-DCFS | N/A | UNITY Replacement | 2022-10-21 | 2026-12-31 | 3143 | 41 | 18370000 |  |  | 18370000 | [6 empty] | 0 | 18370000 |  |  | 8554.95 | 134739.35 | 1523983.62 | 85110 |  | 1752387.92 | 16617612.08 | 9.539% |  |  | 1001100 | 4493782.08 | 1875381 | 1875381 | 1875381 | 1875381 | 3621206 |  | 16617612.08 | 0 | On Track | New contract to provide design, development, and implementation services for a new comprehensive child welfare information system was approved at May BOE. Kickoff meeting scheduled for 06/8/26. Projections are based on CCWIS budget for design and implementation, project management and independent valuation.
409 | DCFS | 23WINIC01 | DHHS-DCFS | N/A | Wraparound Authority/ intensive Care Coordination | 2022-08-18 | 2026-12-31 | 3145-FY23, 3146-FY24 | 01, 40 | 7314984 |  | 7335048 | 14650032 |  |  |  | 6250348 |  |  | 6250348 | 8399684 |  |  |  | 2545174.34 | 4389270 | 1134000 |  | 8068444.34 | 331239.66 | 96.06% |  |  | 24605.66 | 55000 | 55000 | 55000 | 55000 | 55000 | 31634 |  | 331239.66 | 0 | On Track | Projections based on the adjusted monthly flat fee of the Magellan contract of $190,000 a month from April 2026 to November 2026 and $169,087.54 a month for December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The June projection includes the expenses from April through June 2026.
[13 empty] | 70932222 | 0 | 401607 | 169817 | 7733119 | 200000 | 0 | 8504543 | 62427679 | 0 | 422.52 | 1606265.15 | 10157766.32 | 15295110.85 | 13802541.24 | 0 | 40862106.08 | 21565572.92 |  | 0 | 444505.66 | 2166356.59 | 5272934.28 | 2654533.16 | 2352968.76 | 2319127.2 | 2315117.2 | 4040029.67 | 0.4 | 21565572.92 | -4.9477e-10
1689087.54
Note on M11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: L01
Note on P11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FY23 not spent and not balanced foward
Note on S12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deob $200,000 FEB26 IFC

## DPBH
[13 empty] | 95990233.1 | 660000 | 5000000 | 3238068 | 2721280 | 288337.5 | 0 | 11907685.5 | 84082547.6 | 0 | 0 | 5181390.45 | 8246904.69 | 25480069.17 | 26840735.99 | 0 | 65749100.3 | 18333447.3 | [11 empty] | 17810810.93
[10 empty] | #REF! | #REF! | #REF! | [9 empty] | 0 | 0 | 5181390.45 | 8246904.69 | 25480069.17 | 26840735.99 | 0 | RFR'S RECEIVED THROUGH 5/21/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 5/26/2026 FOR JULY-APRIL | 2026-05-16 | 2026-06-15 | 2026-07-15 | 2026-08-14 | 2026-09-13 | 2026-10-13 | 2026-11-12 | 2026-12-12 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
406 | DPBH | 22BHCGM01 | DHHS-DPBH | N/A | CONTRACT MANAGEMENT SYSTEM | 2022-05-05 | 2026-06-30 | 3223 | 19 | 477606 |  |  | 477606 | [6 empty] | 0 | 477606 |  |  | 326628 | 60282 | 39664.2 | 120 |  | 426694.2 | 50911.8 | 89.34% | N/A | 810.23 | 5671.57 | 7082.5 | 7082.5 | 7082.5 | 7082.5 | 8050 | 8050 |  | 50911.8 | 0 | On Track | A request to extend the performance period to 12/30/26 has been submitted, to ensure that future approved Agate Change Requests will be able to be completed and paid for through 12/30/26. Funds were allocated to the Service Enhancement deliverable to pay for approved Change Requests.
406 | DPBH | 22BHSTF01b-c | DHHS-DPBH | N/A | DPBH STAFFING for ARPA Reporting-SFY24 & SFY25 | 2023-07-01 | 2027-03-31 | 3223 | 01 / 18 | 552445 | 404873 |  | 957318 | [6 empty] | 0 | 957318 |  |  |  | 249208.08 | 252955.18 | 207439.22 |  | 709602.48 | 247715.52 | 74.12% | N/A | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 71715.52 | 247715.52 | 0 | On Track | Project performance period extended for continued work and support of completing project tasks, Performing final reconcilliation, and submitting all final reporting. Project on-track to fully expend all funds. Projections based on current expenditure trends.
406 | DPBH | 23CFAEP01 | DHHS-DPBH | N/A | EPIDEMIOLOGIST | 2022-10-20 | 2026-12-31 | 3219 | 34 | 5000000 |  |  | 5000000 | [6 empty] | 0 | 5000000 |  |  | 5642.56 | 191705.75 | 1410887.74 | 1292032.13 |  | 2900268.18 | 2099731.82 | 58.01% | N/A | 190607.98 | 272731.97 | 272731.97 | 272731.97 | 272731.97 | 272731.97 | 272731.97 | 272732.02 |  | 2099731.82 | 0 | On Track | Kristen Clements-Nolle: PhD (3), MS HAB (6), MPH Epi (3), Grad Special MPH Epi (2), Epidemiology and Biostatistics Certificate (2), Grad Special Epi and Biostatistics Certificate (1), Online Public Health Data Management and Analysis Certificate (7), Undergraduate Public Health (7), Graduate Assistant MS HAB (3), Graduate Assistant MPH Epi (7), Graduate Assistant Online MPH (1). Brian Labus: All program staff, and all three member of cohort 2 are currently in the program. Two of three people from cohort 1 completed the 12 months, one left a month early to take a full time position. Projections based on previous expenditures and coordiation with subrecipient. Expected to fully ewxpend funds.
406 | DPBH | 23EMGCS01 | DHHS-DPBH-CRISIS RESPONSE | N/A | EMERGENCY CRISIS CARE (Transfer 5 million to DCFS) | 2022-07-01 | 2026-06-30 | 3165 | 64 | 10000000 |  |  | 10000000 | 0 | 5000000 | 1900000 |  |  |  | 6900000 | 3100000 |  |  | 57796.22 | 2079879 | 698605.6 | 249285.96 |  | 3085566.78 | 14433.22 | 99.53% | N/A | 2026-05-16: 957.22; 2026-06-15: 13476 |  | 14433.22 | 2.6012e-10 | On Track | This funding stream did receive a approved extension to end on June 30, 2026. Our Seven Hills provider was able to expend a majority of their award hoever it did end at the December. We are currently getting a new award for the remaining balance $13,476 to Desert Parkway to expend quickly before June 2026.
406 | DPBH | 23GIDTR01 | DHHS-DPBH | N/A | GENOMIC INFECTIOUS DISEASE TRACKING | 2022-10-20 | 2026-06-30 | 3219 | 35 | 1500000 |  |  | 1500000 | [6 empty] | 0 | 1500000 |  |  |  | 131435.79 | 943395.25 | 425168.62 |  | 1499999.66 | 0.34 | 100% | N/A | 2026-05-16: 0; 2026-06-15: 0 |  | 0 | -0.34 | On Track | Project Complete. Closeout activities in process.
406 | DPBH | 23HCWSS02 | DHHS-DPBH | N/A | Health Care Workforce Scholarships (Transferred from DHCFP) | 2023-06-14 | 2026-12-31 | 3234 | 22 | 5494300 |  |  | 5494300 | [6 empty] | 0 | 5494300 |  |  |  | 201861.5 | 1819585.17 | 2262469.92 |  | 4283916.59 | 1210383.41 | 77.97% | N/A | 147779.79 | 237668.36 | 147176.06 | 147176.06 | 147176.06 | 127802.36 | 127802.36 | 127802.36 |  | 1210383.41 | 0 | On Track | Healthy Communities Coalition 31 scholarship recipients total award. 100% spent down. UNR Larson Institute 26 scholarship recipients CHW, 15 English Doula, 17 Spanish Doula scholarship recipients, 20 scholarship applicants accepted training scholarships. UNR Integration 6 fellowships. Nevada Primary Care 11 Scholarships PCP’s, 1 Preceptor 1 MA learners, 9 EKG learners. High Sierra AHEC 15 scholarships for Spring 2026 semester. 5 Ambassadors, 1 Scholar. UNR CASAT Supervision: 13 new licensed PRSS-S; 1 new licensed ADG Supervisors. UNLV BeHere 23 scholarship recipients. UNR Resilience, Praveen: 9 Public Health Certificates, 9 Full time online MPH program. Dr. Sharma 154 (Undergraduate: 28; Master's: 64; Doctoral: 62); In addition, all total GA-ships have also been awarded: 15(Master's=9; Doctoral=6); Project is On Track and expected to fully spend down by end of project period.
406 | DPBH | 23IBCLC02 | DHHS-DPBH | N/A | International Board Certified Lactation Consultants | 2023-06-15 | 2026-12-31 | 3234 | 21 | 666000 |  | 0 | 666000 | [6 empty] | 0 | 666000 |  |  |  | 4997.96 | 157255.49 | 212652.28 |  | 374905.73 | 291094.27 | 56.29% | N/A | 23904.88 | 39841.5 | 39841.5 | 39841.5 | 39841.5 | 34613.09 | 34613.09 | 38597.21 |  | 291094.27 | 0 | On Track | UNLV Pipeline Southern Nevada latch clinic has officially started with adding two extra days that began on May 1st. One at the Healthy Living Institute, and adding another day at UNLV Pediatrics. The pathway 3 mentees have also attended a breastfeeding workshop hosted by the NV Breastfeeding Coalition to increase their knowledge and skill set. Has also been approached with the opportunity to work with the city of Henderson to have our mentees teach breastfeeding education this summer. Project is On Track and expected to fully spend down by end of project period.
406 | DPBH | 23LCCMS01 | DHHS-DPBH | N/A | Lakes Crossing Camera System | 2022-08-18 | 2026-04-30 | 3645 | 61 | 1462644 |  |  | 1462644 |  |  |  |  | 288337.5 |  | 288337.5 | 1174306.5 |  |  | 24377.24 | 103040.13 | 888600.13 | 115031.97 |  | 1131049.47 | 43257.03 | 96.32% | N/A | [9 empty] | 0 | -43257.03 | Savings Identified | The 23LCCMS01 project has been completed. A request to deobligate the remaining balance of $43,257.03 and redirect the savings to 24FPROS01 was submitted on 4/27/2026.
406 | DPBH | 23LRHA01 | DHHS-DPBH | N/A | Local & Regional Authorities Washoe, Carson, Churchill & SNHD (Merged) | 2022-08-17 | 2026-12-31 | 3234 | 23 | 20800000 |  |  | 20800000 | [6 empty] | 0 | 20800000 |  |  | 4661930.94 | 2517080.94 | 3263651.78 | 6352663.44 | 0 | 16795327.1 | 4004672.9 | 80.75% | N/A | 133067.72 | 399203.16 | 578733.67 | 578733.67 | 578733.67 | 723417.08 | 723417.09 | 289366.84 |  | 4004672.9 | 0 | On Track | Washoe: NNPH is on time and under budget - The ribbon cutting ceremony occurred April 23. An additional SOW has been submitted for review and approval. Carson: CCHHS On track for project completion in November 2026. Churchill: The project is 95% to completion. On target to complete project as expected.
406 | DPBH | 23NBSTR01 | DHHS-DPBH | N/A | UNR NSPHL Newborn | 2022-10-20 | 2026-10-31 | 3222 | 33 | 3953689 |  |  | 3953689 | [6 empty] | 0 | 3953689 |  |  |  | 820927.41 | 1889733.67 | 968761.76 |  | 3679422.84 | 274266.16 | 93.06% | N/A | 117895.36 | 13030.9 | 39092.7 | 19546.35 | 26061.8 | 58639.05 |  |  |  | 274266.16 | 0 |  | Spend down is on track; 3 of the 5 remaining disorders will be added to the panel after the building certificate of occupancy is granted in October 2026 as equipment can't be set up until they are in the new building. NSPHL states they will completely spend down by end of performance period.
406 | DPBH | 23RCCLV01 | DHHS-DPBH | N/A | RECUPERATIVE CARE CENTER EXPANSION | 2022-10-20 | 2026-09-30 | 3161 | 63 | 10000000 |  |  | 10000000 | [6 empty] | 0 | 10000000 |  |  |  | 0 | 1648607.93 | 7431628.33 |  | 9080236.26 | 919763.74 | 90.8% | N/A | 183952.75 | 275929.13 | 229940.94 | 137964.56 | 91976.36 |  |  |  |  | 919763.74 | 0 | On Track | Project is ongoing and spending has increased rapidly, with $9,080,236.26 in expenditures as of June, 2026. Expected to fully spend down by end of project period. Projections based previously expended funds and coordination with subrecipient.
406 | DPBH | 23RHSCC01 | DHHS-DPBH | N/A | Reproductive Health Services | 2023-01-01 | 2026-12-31 | 3224 | 01, 15 | 6446148 |  |  | 6446148 | [6 empty] | 0 | 6446148 |  |  | 105015.49 | 1191335.83 | 1489526.75 | 774530.1 |  | 3560408.17 | 2885739.83 | 55.23% | N/A | 71591.84 | 365368.85 | 408129.86 | 408129.86 | 408129.86 | 408129.86 | 408129.86 | 408129.84 |  | 2885739.83 | 0 | On Track | All three subgrantees have submitted spend plans for the entirety of the project period; spend plans submitted are based by SFY, hence the projections have been broken out monthly based on subrecipients projections. Spend plans ascertain they will fully expend their award amounts by the end of the project period, December 31, 2026.
406 | DPBH | 24FPROS01 | DHHS-DPBH | N/A | Forensic Professional Services - Lake Crossing | 2023-12-13 | 2026-12-31 | 3645 | 62 | 4920000 |  |  | 4920000 | 660000 |  | 744094 |  |  |  | 1404094 | 3515906 |  |  |  | 127478.69 | 1251293.04 | 1132091.15 |  | 2510862.88 | 1005043.12 | 71.41% | N/A | 125630.39 | 125630.39 | 125630.39 | 125630.39 | 125630.39 | 125630.39 | 125630.39 | 125630.39 |  | 1005043.12 | 0 | On Track | Project is on track and has become destination for de-obligated funds to support ability to spend. A request to deobligate the remaining balance of $43,257.03 from 23LCCMS01 and redirect the savings to 24FPROS01 was submitted on 4/27/2026. A request is to transfer $479,379 from 24SNFLT01 to 24FPROS01. The associated work programs (#27FRF31611 and #27FRF36452) are in process. Additional allocations to spend plan will be included in projections when funds become available for project.
406 | DPBH | 24JBMHP01 | DHHS-DPBH | N/A | Forensic Jail Based Mental Health Programs (SNAMHS/NNAMHS) | 2023-12-13 | 2026-12-31 | 3161 | 64 | 14905281 | 3691097.1 |  | 18596378.1 | [6 empty] | 0 | 18596378.1 |  |  |  | 375456.73 | 9082223.3 | 4927185.01 |  | 14384865.04 | 4211513.06 | 77.35% | N/A | 1121255.6 | 735775.59 | 631540.71 | 564094.62 | 441465.35 | 340290.2 | 266724.65 | 110366.34 |  | 4211513.06 | 0 | On Track | Project is on track to fully spend down by the end of the performance period. Continues to be an option for re-allocated funds due to continued ability to spend additional funds.
406 | DPBH | 24SNFLT01 | DHHS-DPBH | N/A | Skilled Nursing Facility - Forensic Long-Term Care | 2023-11-17 | 2026-12-31 | 3161 | 65 | 5716150 |  |  | 5716150 |  |  | 593974 | 2721280 |  |  | 3315254 | 2400896 |  |  |  | 192214.88 | 644083.94 | 489676.1 |  | 1325974.92 | 1074921.08 | 55.23% | N/A | 115504.2 | 106659.86 | 62229.67 | 62229.67 | 62229.67 | 62229.67 | 62229.67 | 62229.67 |  | 595542.08 | -479379 | Savings Identified | 24SNFLT01 savings are due to competitive rates with current community providers. A request is to transfer $479,379 from 24SNFLT01 to 24FPROS01. The associated work programs (#27FRF31611 and #27FRF36452) are in process.
[13 empty] | 95990233.1 | 660000 | 5000000 | 3238068 | 2721280 | 288337.5 | 0 | 11907685.5 | 84082547.6 | 0 | 0 | 5181390.45 | 8246904.69 | 25480069.17 | 26840735.99 | 0 | 65749100.3 | 18333447.3 |  | 0 | 2254957.96 | 2612987.28 | 2564129.97 | 2385161.15 | 2223059.13 | 2182566.17 | 2051329.08 | 1464904.67 | 71715.52 | 17810810.93 | -522636.37
Note on P7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending Grant Realignment WP for $2,896,697 reduction in authority (DK) Reply: $5,000,000 - transferred to DCFS under WP# 23FR314521
Note on Q7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agency Submitted DeOb for $2,896,697 that was signed off. Agency sent email to the COVID19 mailbox Requesting to Retract DeOB. Dan told Amy @ ARPA Admin Mtng 3.14.24 and she is checking with Jim Wells. Reply: $2.8 retracted but agency is giving up 1.9 per J. Wells. WP 24FR316504 (-903,303) combined with an L01 of 3,945,507 reduces the award by the 1.9 million. Reply: WP #24FR316504 $903,303
Note on S11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Partial Deob $288,337.50 Transfer to Jail Based 24JBMHP01
Note on O16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deob WP 24FRF36453
Note on Q16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: De-Obligation #24FR132776 $744,094 - June 2024 IFC Reply: Agency De-Ob WP# 24FRF36454
Note on L17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Supplemental#1=$2,939,148 & Supplemental #2 =$221,588.96 Supplemental #3= $530,360.14 Reply: Supplemental #2+#3 = $751,950.10 26FRF31613 FEB-IFC
Note on Q18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WP#24FR132777 De-Obligation $2,070,848 June 2024 IFC Reply: Agency De-Ob WP#24FRF31618 - Revised to $593,974
Note on U18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WP#24FRF31618 June 2024 IFC

## DSS
[13 empty] | 91010328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91010328 | 0 | 0 | 11418760.28 | 22299776.73 | 19829864.85 | 19403319.96 | 0 | 72951721.82 | 18058606.18 | [11 empty] | 18058606.18
[10 empty] | #REF! | #REF! | #REF! | [9 empty] | 0 | 0 | 11418760.28 | 22299776.73 | 19829864.85 | 19403319.96 | 0 | RFR'S RECEIVED THROUGH 5/21/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 5/26/2026 FOR JULY-APRIL | 2026-05-16 | 2026-06-15 | 2026-07-15 | 2026-08-14 | 2026-09-13 | 2026-10-13 | 2026-11-12 | 2026-12-12 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
407 | DSS | 23ACNVM01 | DHHS-DSS | N/A | ACCESS NEVADA MODERNIZATION No Wrong Door Single Web Portal | 2022-10-25 | 2026-12-31 | 3228 | 53 | 3112296 |  | 9387704 | 12500000 | [6 empty] | 0 | 12500000 |  |  |  | 4148997.17 | 3964544.82 | 1894081.81 |  | 10007623.8 | 2492376.2 | 80.06% | 0 | 184527.06 | 1637126 | 350625 | 111787 | 124320 | 83991.14 | 0 | 0 |  | 2492376.2 | 0 | On Track | Projections are based on monthly deliverables and remaining billing to address M&O production defect resolution through 12/31/2026
407 | DSS | 23CHDIF01 | DHHS-DSS | N/A | CHILD CARE INFRASTRUCTURE | 2022-05-06 | 2026-12-31 | 3267 | 55 | 30000000 |  |  | 30000000 | [6 empty] | 0 | 30000000 |  |  | 8455742.56 | 11363038.52 | 5323464.92 | 3958163.78 |  | 29100409.78 | 899590.22 | 97% | 0 | 387477.73 | 343559.14 | 138953.84 | 10008.64 | 9757.79 | 6256.84 | 3576.24 |  |  | 899590.22 | 1.1642e-09 | On Track | All subrecipients are on track for spending.
407 | DSS | 23NOMAD01 | DHHS-DSS | N/A | NOMADS MODERNIZATION | 2022-10-20 | 2026-12-31 | 3228 | 64 | 48510328 |  |  | 48510328 | [6 empty] | 0 | 48510328 |  |  | 2963017.72 | 6787741.04 | 10541855.11 | 13551074.37 |  | 33843688.24 | 14666639.76 | 69.77% | 0 | 508374.82 | 5562588.36 | 2517341.9 | 2517341.9 | 1517341.9 | 1475709.88 | 317941 | 250000 |  | 14666639.76 | 0 | On Track | Projections are based on monthly contractual/MSA deliverables, Phase III and M&O production defect resolution through 12/31/2026
[13 empty] | 91010328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91010328 | 0 | 0 | 11418760.28 | 22299776.73 | 19829864.85 | 19403319.96 | 0 | 72951721.82 | 18058606.18 |  | 0 | 1080379.61 | 7543273.5 | 3006920.74 | 2639137.54 | 1651419.69 | 1565957.86 | 321517.24 | 250000 | 0 | 18058606.18 | 1.1642e-09